## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 |  | 1 | Data was collected from multiple heterogeneous sources including structured databases (CSV, SQL), semi-structured files (JSON, XML), and unstructured sources such as documents, reports, and web contea |  |  |  | 3- Completed
1 |  | 2 | Ingested data was validated to identify missing values, schema mismatches, duplicate records, and corrupted entries before further processing. |  | 1 |  | 3- Completed
1 |  | 3 | Noise, inconsistencies, duplicates, and incomplete records were removed. Missing values were handled using appropriate strategies such as imputation or exclusion. |  | 1 |  | 3- Completed
1 |  | 4 | Data fields were standardized into a consistent format (naming conventions, date formats, units, categorical values) to ensure uniformity across all datasets. |  | 1 |  | 3- Completed
2 |  | 5 | A common schema was designed, and all incoming data sources were mapped into this unified schema to support seamless integration and interoperability. |  | 1 |  | 3- Completed
2 |  | 6 | A common schema was designed, and all incoming data sources were mapped into this unified schema to support seamless integration and interoperability. |  | 2 |  | 3- Completed
2 |  | 7 | Cleaned and normalized data was converted into JSON format to enable flexible downstream processing and easy integration with AI pipelines. |  | 2 |  | 3- Completed
2 |  | 8 | Key entities such as organizations, people, locations, events, products, and concepts were automatically extracted using NLP techniques. |  | 2 |  | 3- Completed
3 |  | 9 | Semantic relationships between extracted entities were identified and defined to represent real-world connections. |  | 2 |  | 3- Completed
3 |  | 10 | Entities and relationships were structured into a graph model, forming a knowledge graph that enables contextual understanding and inference. |  | 3 |  | 3- Completed
3 |  | 11 | Large textual content was split into semantically meaningful chunks to optimize embedding generation and retrieval performance. |  | 3 |  | 3- Completed
3 |  | 12 | Text chunks and entities were converted into vector embeddings using a pre-trained embedding model for semantic representation. |  | 3 |  | 3- Completed
4 |  | 13 | Generated embeddings were stored in a vector database (such as FAISS) to enable fast and scalable similarity search. |  | 3 |  | 3- Completed
4 |  | 14 | A semantic search layer was implemented to retrieve relevant information based on user queries using vector similarity. |  | 4 |  | 3- Completed
4 |  | 15 | Vector-based semantic search was combined with knowledge graph traversal to improve accuracy, context, and explainability of results. |  | 4 |  | 3- Completed
4 |  | 16 | Retrieved knowledge was provided as context to a large language model to generate accurate, grounded, and context-aware responses. |  | 4 |  | 3- Completed
5 |  | 17 | To provide an interactive, intuitive visualization layer that allows users to explore the knowledge graph, analyze relationships, perform semantic search, and view AI-generated insights in real time. |  | 4 |  | 3- Completed
5 |  | 18 | To enhance system transparency and usability by introducing confidence metrics for AI outputs and enabling direct file downloads from the underlying database through the UI. |  | 5 |  | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
1 | U01 | Data was collected from multiple heterogeneous sources including structured databases (CSV, SQL), semi-structured files (JSON, XML), and unstructured sources such as documents, reports, and web contea | 30//nov/25 | 2025-12-04 |  | Data Collection | 3- Completed
1 | U02 | Ingested data was validated to identify missing values, schema mismatches, duplicate records, and corrupted entries before further processing. | 2025-11-30 | 2025-12-04 |  | Data Collection | 3- Completed | 2
2 | U03 | Noise, inconsistencies, duplicates, and incomplete records were removed. Missing values were handled using appropriate strategies such as imputation or exclusion.Data fields were standardized into a consistent format (naming conventions, date formats, units, categorical values) to ensure uniformity across all datasets. | 2025-12-04 | 2025-12-11 |  | Coding | 3- Completed | 5
2 | U04 | A common schema was designed, and all incoming data sources were mapped into this unified schema to support seamless integration and interoperability.A common schema was designed, and all incoming data sources were mapped into this unified schema to support seamless integration and interoperability. | 2025-12-11 | 2025-12-18 |  | Coding | 3- Completed | 6
SPRINT 2 BACKLOG
2 | U05 | Cleaned and normalized data was converted into JSON format to enable flexible downstream processing and easy integration with AI pipelines.Cleaned and normalized data was converted into JSON format to enable flexible downstream processing and easy integration with AI pipelines. | 2025-12-11 | 2025-12-18 |  | Coding | 3- Completed | 2
3 | U06 | Key entities such as organizations, people, locations, events, products, and concepts were automatically extracted using NLP techniques.Semantic relationships between extracted entities were identified and defined to represent real-world connections. | 2025-12-11 | 2025-12-18 |  | Coding | 3- Completed | 7
SPRINT 3 BACKLOG
3 | U07 | Entities and relationships were structured into a graph model, forming a knowledge graph that enables contextual understanding and inference.Large textual content was split into semantically meaningful chunks to optimize embedding generation and retrieval performance. | 2025-12-18 | 2025-12-27 |  | Coding | 3- Completed | 8
4 | U08 | Text chunks and entities were converted into vector embeddings using a pre-trained embedding model for semantic representation.Generated embeddings were stored in a vector database (such as FAISS) to enable fast and scalable similarity search. | 2025-12-27 | 2026-01-03 |  | Coding | 3- Completed | 10
4 | U09 | A semantic search layer was implemented to retrieve relevant information based on user queries using vector similarity.Vector-based semantic search was combined with knowledge graph traversal to improve accuracy, context, and explainability of results. | 2026-01-03 | 2026-01-10 |  | Coding | 3- Completed | 8
SPRINT 4 BACKLOG
4 | U10 | Retrieved knowledge was provided as context to a large language model to generate accurate, grounded, and context-aware responsesTo provide an interactive, intuitive visualization layer that allows users to explore the knowledge graph, analyze relationships, perform semantic search, and view AI-generated insights in real time.. | 2026-01-11 | 2026-01-18 |  | Coding | 3- Completed | 9
SPRINT 5 BACKLOG
5 | U11 | To enhance system transparency and usability by introducing confidence metrics for AI outputs and enabling direct file downloads from the underlying database through the UI. | 2026-01-18 | 2026-01-27 |  | Design | 3- Completed | 10

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 2026-03-01 | Data was collected from multiple heterogeneous sources including structured databases (CSV, SQL), semi-structured files (JSON, XML), and unstructured sources such as documents, reports, and web contea | Begin the work
1 | 2026-07-04 | Ingested data was validated to identify missing values, schema mismatches, duplicate records, and corrupted entries before further processing. | Start the Work
2 | 2026-04-01 | Cleaned and normalized data was converted into JSON format to enable flexible downstream processing and easy integration with AI pipelines.Cleaned and normalized data was converted into JSON format to enable flexible downstream processing and easy integration with AI pipelines. | created entity trples
2 | 2026-07-03 | Key entities such as organizations, people, locations, events, products, and concepts were automatically extracted using NLP techniques.Semantic relationships between extracted entities were identified and defined to represent real-world connections. | entity relation
3 | 2026-02-01 | Entities and relationships were structured into a graph model, forming a knowledge graph that enables contextual understanding and inference.Large textual content was split into semantically meaningful chunks to optimize embedding generation and retrieval performance. | Grpah generation
3 | 2026-05-02 | Text chunks and entities were converted into vector embeddings using a pre-trained embedding model for semantic representation.Generated embeddings were stored in a vector database (such as FAISS) to enable fast and scalable similarity search. | chunks
3 | 2026-07-05 | A semantic search layer was implemented to retrieve relevant information based on user queries using vector similarity.Vector-based semantic search was combined with knowledge graph traversal to improve accuracy, context, and explainability of results. | emebedding generation anf vector database
4 | 2026-05-01 | Retrieved knowledge was provided as context to a large language model to generate accurate, grounded, and context-aware responsesTo provide an interactive, intuitive visualization layer that allows users to explore the knowledge graph, analyze relationships, perform semantic search, and view AI-generated insights in real time.. | Grpah generation
4 | 2026-07-06 | A semantic search layer was implemented to retrieve relevant information based on user queries using vector similarity.Vector-based semantic search was combined with knowledge graph traversal to improve accuracy, context, and explainability of results. | UI
5 | 2026-07-01 | To enhance system transparency and usability by introducing confidence metrics for AI outputs and enabling direct file downloads from the underlying database through the UI. | UI

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-11-30 | 2025-12-18 |  | Data Collection
2 | 2 | 2025-12-18 | 2026-01-03 |  | Ingestion
3 | 3 | 2026-01-11 | 2026-01-18 |  | Data triples and Entity Extarction
4 | 4 | 2026-01-18 | 2026-01-20 |  | creating knwoledge graph and hybrid vector database and embeddings
5 | 5 | 2026-01-20 | 2026-01-27 |  | implement ui
6
7